## Submittal Log
MASTER SUBMITTAL LOG
2005 HDOT Standard Specifications for Road and Bridge Construction
Project: |  | Contract No.: |  | Contractor: |  | Resident Engineer: |  | Date Prepared:
SECTION 1 — PRECONSTRUCTION SUBMITTALS (§108.03) ¦ No progress payments until all items accepted in writing
# | Description | Spec Ref | Date Submitted | Date Accepted | Status | Notes
PRE-01 | List of Superintendent and Supervisory Personnel | 108.03(1) |  |  | PENDING
PRE-02 | Name(s) Authorized to Sign for Contractor | 108.03(2) |  |  | PENDING
PRE-03 | Work Schedule | 108.03(3) |  |  | PENDING
PRE-04 | Initial Progress Schedule (TSLD) — see §108.06 | 108.03(4) |  |  | PENDING
PRE-05 | Water Pollution and Siltation Control Plan | 108.03(5) |  |  | PENDING
PRE-06 | Solid Waste Disposal Form | 108.03(6) |  |  | PENDING
PRE-07 | Tax Rates | 108.03(7) |  |  | PENDING
PRE-08 | Insurance Rates | 108.03(8) |  |  | PENDING
PRE-09 | Certificate of Insurance | 108.03(9) |  |  | PENDING
PRE-10 | Schedule of Agreed Prices | 108.03(10) |  |  | PENDING
PRE-11 | List of Suppliers | 108.03(11) |  |  | PENDING
SECTION 2 — SHOP DRAWINGS & DESCRIPTIVE DATA (§105.02–05.04) ¦ 30-day Engineer review ¦ Resubmit within 15 days of rejection
# | Description | Spec Ref | Type | Copies Req'd | HI PE Stamp? | Date Submitted | Engineer Due (30d) | Date Returned | Status | Resubmit Due (15d) | Notes
SD-01 | HMA Job-Mix Formula (JMF) | 401.02(B-C) | Shop Drawing | 6 | No |  |  |  | PENDING |  | Must be accepted before HMA production begins
SD-02 | Traffic Control Plan | 104.09 | Shop Drawing | 6 | Yes |  |  |  | PENDING |  | HI PE stamp required; submit early
SD-03 | Erosion / Water Pollution Control Plan | 107.16 | Descriptive | 6 | No |  |  |  | PENDING
SD-04 | Structural Shop Drawings | 501+ | Shop Drawing | 6 | Yes |  |  |  | PENDING |  | HI PE stamp required for all structural
SD-05 | Utility Protection / Relocation Plan | 104.11 | Shop Drawing | 6 | No |  |  |  | PENDING |  | Submit before earthwork begins
SD-06 | Cold Planing Plan | 415 | Descriptive | 6 | No |  |  |  | PENDING
SD-07 | Slurry Seal Mix Design | 404 | Descriptive | 6 | No |  |  |  | PENDING |  | If applicable
SD-08 | PCC Mix Design | 411 | Descriptive | 6 | No |  |  |  | PENDING |  | If applicable
SD-09 | [Add project-specific item] |  |  | 6 |  |  |  |  | PENDING
SD-10 | [Add project-specific item] |  |  | 6 |  |  |  |  | PENDING
SECTION 3 — MATERIAL SAMPLES & CERTIFICATIONS (§106.04–106.05) ¦ 45-day review for samples ¦ Submit certificates before material incorporation
# | Description | Spec Ref | Type | Date Submitted | Engineer Due (45d) | Date Returned | Status | Resubmit Due (15d) | Notes
MAT-01 | Asphalt Cement Certificate of Compliance (PG 64-16) | 401.02(A) / 702.01 | Certificate of Compliance |  |  |  | PENDING |  | Required before HMA production
MAT-02 | Aggregate for HMA — Sample | 401.02(A) / 703.09 | Material Sample |  |  |  | PENDING |  | 45-day review clock applies
MAT-03 | Tack Coat — Certificate of Compliance | 407 / 702.04 | Certificate of Compliance |  |  |  | PENDING |  | Required before overlay
MAT-04 | Slurry Seal — Mix Design / Sample | 404 | Material Sample |  |  |  | PENDING |  | If applicable
MAT-05 | PCC — Concrete Mix Design | 411 / 701 | Material Sample |  |  |  | PENDING |  | If applicable
MAT-06 | Structural Steel / Rebar — Certificate of Compliance | 501+ / 709 | Certificate of Compliance |  |  |  | PENDING |  | Buy America certification required on Federal-Aid projects (§106.11)
MAT-07 | [Add project-specific material] | [5 empty] | PENDING
MAT-08 | [Add project-specific material] | [5 empty] | PENDING

## Legend & Notes
STATUS CODES
PENDING | Not yet submitted
SUBMITTED | Submitted; review clock running
ACCEPTED | Engineer accepted; work may proceed
ACCEPTED W/ COMMENTS | Accepted with conditions noted on return
REJECTED | Returned; Contractor must resubmit within 15 days
RESUBMITTED | Resubmitted; review clock restarted
VOID | Not applicable to this project
KEY SPEC REFERENCES
§105.02–05.04 | Shop drawings / descriptive data: 6 copies; 30-day review; resubmit within 15 days of rejection
§106.04–06.05 | Material samples: 45-day review; Engineer acceptance ≠ final conformance
§108.03 | 11 preconstruction items required; no progress payments until all accepted in writing
§105.03 | Shop drawings requiring PE stamp must be sealed by a Hawaii-licensed PE (not out-of-state)
§106.11 | Buy America: steel/iron on Federal-Aid projects must be American-made; certify before incorporation
§104.02 | Engineer marks on returned submittals are NOT change orders; follow 104.02 if you believe otherwise